## Overview
Audio-to-Lyrics Alignment MVP — Project Dashboard
Project | Live Audio-to-Lyrics Alignment Engine
Delivery model | 4 one-week sprints with Codex
Target duration | 1 month
Architecture | Modular monolith with hexagonal boundaries
Primary runtime | Python 3.11 + ONNX Runtime
Presentation bridge | OSC to FreeShow / ProPresenter
MVP boundary | One selected song at a time
Total Tasks | Completed | In Progress | Blocked | Not Started | Overall Progress | Open Risks | Sprint
27 | 0 | 0 | 0 | 26 | 0% | 6 | Not started
MVP Success Metric | Target | Current | Status
Correct slide transitions | ≥ 90% |  | Not Measured
False transitions per song | < 3 |  | Not Measured
Median timestamp error | < 1.5 sec |  | Not Measured
End-to-end latency | < 700 ms |  | Not Measured
Recovery time | < 8 sec |  | Not Measured
Crash-free full-song run | 100% |  | Not Measured

## Timeline
One-Month Delivery Timeline
Sprint | Week | Goal | Start Date | End Date | Milestone | Exit Gate | Status | Progress
Sprint 1 | Week 1 | Architecture, project foundation, audio ingestion | 2026-07-13 | 2026-07-19 | Audio foundation | 30-minute stable audio capture and passing checks | Not Started | 0%
Sprint 2 | Week 2 | ONNX feature extraction and reference profiles | 2026-07-20 | 2026-07-26 | Feature pipeline | Finite compatible features; inference faster than real time | Not Started | 0%
Sprint 3 | Week 3 | Offline and online alignment plus slide stability | 2026-07-27 | 2026-08-02 | Real-time tracker | Median error < 1.5 sec and stable slide decisions | Not Started | 0%
Sprint 4 | Week 4 | OSC integration, end-to-end testing, pilot | 2026-08-03 | 2026-08-09 | Pilot-ready MVP | Complete song run, OSC triggers, no random transitions | Not Started | 0%

## Sprint Backlog
Sprint Backlog and Task Tracker
Sprint | Task ID | Task | Scope / Deliverable | Owner | Priority | Estimate (hrs) | Status | % Complete | Acceptance Criteria | Dependency
Sprint 1 | S1-01 | Scaffold repository architecture | Create src/domain, application, ports, adapters, tools, tests | Senior Python Engineer | High | 3 | Not Started | 0% | Repository imports cleanly and architecture boundaries are documented | None
Sprint 1 | S1-02 | Configure Python project | Add pyproject.toml, Ruff, MyPy, Pytest, coverage | Senior Python Engineer | High | 2 | Not Started | 0% | All tooling runs successfully | S1-01
Sprint 1 | S1-03 | Define domain models and ports | AudioChunk, FeatureFrame, MatchResult, SlideCommand and protocols | Senior Python Engineer | High | 4 | Not Started | 0% | Domain layer has no infrastructure imports | S1-01
Sprint 1 | S1-04 | Implement simulated audio source | Deterministic 16 kHz mono float32 chunks | Senior Python Engineer | High | 5 | Not Started | 0% | Chunk shape, dtype, sequence and shutdown tests pass | S1-03
Sprint 1 | S1-05 | Implement bounded audio queue | Non-blocking enqueue with oldest-chunk drop policy | Senior Python Engineer | High | 4 | Not Started | 0% | Queue overflow never blocks producer | S1-04
Sprint 1 | S1-06 | Implement SoundDevice source | Safe callback, device validation, silence and clipping metrics | Senior Python Engineer | High | 8 | Not Started | 0% | 30-minute stability test passes | S1-05
Sprint 1 | S1-07 | Add lifecycle and metrics | Graceful shutdown, structured logging, runtime counters | Senior Python Engineer | Medium | 4 | Not Started | 0% | SIGINT/SIGTERM stop all workers safely | S1-05
Sprint 2 | S2-01 | Inspect ONNX model metadata | Resolve dynamic input/output names and providers | ML Engineer | High | 4 | Not Started | 0% | Metadata is logged and validated at startup | S1-02
Sprint 2 | S2-02 | Implement ONNX feature extractor | Normalize audio and adapt common tensor shapes | ML Engineer | High | 10 | Not Started | 0% | Outputs finite 2D frame features | S2-01
Sprint 2 | S2-03 | Implement simulated extractor | Deterministic feature frames without model | Senior Python Engineer | Medium | 4 | Not Started | 0% | CI works without model file | S1-04
Sprint 2 | S2-04 | Build reference profile CLI | Convert WAV to reference_features.npy, profile.json, metadata.json | Senior Python Engineer | High | 10 | Not Started | 0% | Profile generation is reproducible | S2-02
Sprint 2 | S2-05 | Validate profiles | Check feature dimensions, intervals and profile versions | QA Engineer | High | 4 | Not Started | 0% | Invalid profiles fail with clear messages | S2-04
Sprint 2 | S2-06 | Benchmark inference | Measure average and max latency | ML Engineer | High | 3 | Not Started | 0% | Inference remains faster than real time | S2-02
Sprint 3 | S3-01 | Implement distance functions | Cosine and normalized Euclidean distance | DSP Engineer | High | 4 | Not Started | 0% | Unit tests cover identical and divergent vectors | S2-02
Sprint 3 | S3-02 | Implement offline subsequence DTW | Baseline evaluator for recorded audio | DSP Engineer | High | 10 | Not Started | 0% | Timestamp error report is generated | S3-01
Sprint 3 | S3-03 | Implement online bounded sDTW | Incremental rows and bounded reference window | DSP Engineer | High | 12 | Not Started | 0% | Memory remains bounded and updates faster than frame rate | S3-02
Sprint 3 | S3-04 | Add confidence and ambiguity logic | Distance-to-confidence, best-vs-second-best margin | ML Engineer | High | 6 | Not Started | 0% | Silence and speech produce low confidence | S3-03
Sprint 3 | S3-05 | Implement tracking state machine | SEARCHING, TRACKING, UNCERTAIN and recovery | Senior Python Engineer | High | 8 | Not Started | 0% | Tracker recovers after temporary loss | S3-03
Sprint 3 | S3-06 | Implement slide controller | Look-ahead, hysteresis, cooldown, duplicate suppression | Senior Python Engineer | High | 8 | Not Started | 0% | One bad frame cannot change a slide | S3-04
Sprint 3 | S3-07 | Create replay evaluation suite | Clean vocal, full band, speech, silence, repeats | QA Engineer | High | 6 | Not Started | 0% | Median error and false jumps are reported | S3-02
Sprint 4 | S4-01 | Implement presentation gateway port | Infrastructure-independent slide command contract | Senior Python Engineer | Medium | 3 | Not Started | 0% | Domain does not depend on OSC | S3-06
Sprint 4 | S4-02 | Implement OSC sender | Separate bounded command queue and JSON payloads | Senior Python Engineer | High | 6 | Not Started | 0% | Network failure does not block alignment | S4-01
Sprint 4 | S4-03 | Integrate live pipeline | Audio → features → alignment → slides → OSC | Senior Python Engineer | High | 10 | Not Started | 0% | A complete song runs end to end | S4-02
Sprint 4 | S4-04 | Add manual override hook | Operator can freeze, jump or reset tracking | Senior Python Engineer | High | 5 | Not Started | 0% | Override responds immediately and safely | S4-03
Sprint 4 | S4-05 | Run controlled pilot | Test mixer feed and presentation client | Church Operator | High | 8 | Not Started | 0% | Pilot metrics and corrections are recorded | S4-03
Sprint 4 | S4-06 | Tune and harden MVP | Fix critical defects, tune thresholds, document limitations | Senior Python Engineer | High | 8 | Not Started | 0% | Pilot-ready release candidate is produced | S4-05

## Codex Prompts
Reusable Codex Prompt Library
Prompt ID | Sprint | Task | When to Use | Prompt | Expected Commit
P-01 | Sprint 1 | Scaffold architecture | Start of repository | Review the repository and establish a modular monolith with hexagonal architecture. Create: - src/lyrics_aligner/domain - src/lyrics_aligner/application - src/lyrics_aligner/ports - src/lyrics_aligner/adapters - tools - tests/unit - tests/integration Requirements: 1. Domain must not import sounddevice, onnxruntime, python-osc, filesystem, or networking code. 2. Add pyproject.toml with Python 3.11, Ruff, MyPy, Pytest, and coverage. 3. Add a minimal CLI entry point and graceful shutdown. 4. Add architecture decision records. 5. Do not implement ONNX, DTW, or OSC yet. 6. Run tests, Ruff, and MyPy. 7. Commit with: chore: establish project foundation | chore: establish project foundation
P-02 | Sprint 1 | Simulated audio source | After architecture setup | Implement only the simulated audio source. Requirements: 1. Follow existing ports and domain models. 2. Produce deterministic 16 kHz mono float32 AudioChunk objects. 3. Make sample rate, block size, frequency, amplitude, and duration configurable. 4. Generate chunks in real time while allowing immediate shutdown. 5. Validate all inputs. 6. Add tests for shape, dtype, sequence numbers, timestamps, determinism, and shutdown. 7. Do not add ONNX, DTW, or OSC. 8. Run pytest, Ruff, and MyPy. 9. Commit with: feat: add simulated audio source | feat: add simulated audio source
P-03 | Sprint 1 | Live audio ingestion | After simulation passes | Implement the SoundDevice audio adapter. Requirements: 1. Use sounddevice.InputStream at 16 kHz, mono, float32, block size 4096. 2. The callback may only copy/flatten audio, capture lightweight metadata, update counters, and perform put_nowait. 3. Never run logging, ONNX, DTW, networking, or file I/O inside the callback. 4. Use a bounded queue. On overflow, drop the oldest chunk and retry once. 5. Validate the selected input device. 6. Track silence, clipping, received chunks, dropped chunks, and queue high-water mark. 7. Add unit tests using mocks and integration-safe tests. 8. Commit with: feat: add non-blocking audio ingestion | feat: add non-blocking audio ingestion
P-04 | Sprint 2 | ONNX extractor | When model file is available | Implement the ONNX feature extractor adapter. Requirements: 1. Load wav2vec2_phoneme.onnx with onnxruntime. 2. Prefer CUDA, then CoreML, then CPU when available. 3. Inspect input and output metadata dynamically. 4. Support [1, samples] and [1, 1, samples] inputs. 5. Support [1, frames, features] and [frames, features] outputs. 6. Normalize waveform and L2-normalize features. 7. Reject non-finite or malformed outputs. 8. Return every feature frame in chronological order. 9. Add deterministic simulation fallback. 10. Add tests and latency metrics. 11. Commit with: feat: add onnx feature extraction | feat: add onnx feature extraction
P-05 | Sprint 2 | Reference profile builder | After extractor works | Create an offline reference profile builder CLI. Inputs: - reference WAV file - slide interval JSON - output directory Outputs: - reference_features.npy - profile.json - metadata.json Requirements: 1. Convert input to 16 kHz mono. 2. Use the production feature extractor. 3. Validate slide ranges, overlaps, feature dimension, and profile version. 4. Make output reproducible. 5. Add tests for invalid profiles and corrupted inputs. 6. Commit with: feat: add reference profile builder | feat: add reference profile builder
P-06 | Sprint 3 | Online sDTW | After offline evaluator is validated | Implement bounded Online Subsequence DTW. Requirements: 1. Use NumPy only for alignment math. 2. Process one incoming feature frame at a time. 3. Preserve previous and current DTW cost rows. 4. Search near the accepted position with small backward and larger forward windows. 5. Prevent paths from leaking across window boundaries. 6. Normalize accumulated cost. 7. Return best frame, timestamp, raw cost, normalized cost, confidence, ambiguity margin, and validity. 8. Add SEARCHING, TRACKING, and UNCERTAIN recovery behavior. 9. Keep memory bounded and benchmark update latency. 10. Add tests for tempo changes, silence, noise, repeats, skips, and recovery. 11. Commit with: feat: add online subsequence dtw tracker | feat: add online subsequence dtw tracker
P-07 | Sprint 3 | Slide controller | After stable match results exist | Implement the slide decision engine. Requirements: 1. Map reference timestamp plus 200 ms look-ahead to a slide. 2. Freeze on low confidence or invalid results. 3. Require configurable consecutive stable matches. 4. Add acceptance/rejection hysteresis. 5. Add cooldown and duplicate suppression. 6. Reject large backward jumps. 7. Keep current slide unchanged during speech, silence, or instrumentation. 8. Add tests around slide boundaries and noisy frames. 9. Commit with: feat: add stable slide decision engine | feat: add stable slide decision engine
P-08 | Sprint 4 | OSC integration | After console slide output works | Implement the OSC presentation adapter. Requirements: 1. Use python-osc SimpleUDPClient. 2. Default host 127.0.0.1, port 7000, path /presentation/trigger-slide. 3. Send JSON string payload containing slide, section, lyrics, timestamp, and confidence. 4. Use a separate bounded command queue and sender worker. 5. Never block the alignment worker on UDP sending. 6. Suppress duplicate commands. 7. Handle send failures without stopping the application. 8. Add console fallback and tests. 9. Commit with: feat: add osc presentation gateway | feat: add osc presentation gateway
P-09 | Sprint 4 | End-to-end integration | Final integration task | Integrate the complete live pipeline. Pipeline: Audio source → bounded audio queue → feature extractor → online sDTW → position stabilizer → slide controller → command queue → OSC gateway. Requirements: 1. Add startup health checks. 2. Add graceful shutdown for every worker. 3. Add configuration CLI. 4. Add compact periodic metrics. 5. Add simulation mode that exercises confidence loss and recovery. 6. Add manual override hooks for freeze, reset, and jump. 7. Add end-to-end replay tests. 8. Document deployment, operation, troubleshooting, and known limitations. 9. Commit with: feat: integrate pilot-ready alignment pipeline | feat: integrate pilot-ready alignment pipeline

## Risks
Project Risk Register
Risk ID | Risk | Impact | Probability | Owner | Mitigation | Status | Review Date
R-01 | Poor audio quality from room mix | High | High | Church Operator | Use a dedicated vocal-heavy mixer matrix; monitor clipping and silence | Open | 2026-07-13
R-02 | Speech-trained model performs poorly on singing | High | High | ML Engineer | Evaluate model on recordings in Sprint 2; keep hybrid feature option in Phase 2 | Open | 2026-07-20
R-03 | Repeated choruses cause wrong section | High | High | DSP Engineer | Use bounded tracking, ambiguity margin, state constraints, and manual override | Open | 2026-07-27
R-04 | Live arrangement differs from reference | High | Medium | DSP Engineer | Allow controlled recovery and document one-reference MVP limitation | Open | 2026-07-27
R-05 | Real-time processing exceeds budget | Medium | Medium | Senior Python Engineer | Benchmark inference and DTW; use bounded queues and NumPy optimization | Open | 2026-07-20
R-06 | False slide transitions during speech | High | Medium | Senior Python Engineer | Confidence freeze, hysteresis, cooldown, consecutive-match validation | Open | 2026-08-03

## Metrics
Pilot and Technical Metrics
Date | Test Scenario | Correct Slides (%) | False Transitions | Median Error (sec) | Latency (ms) | Recovery Time (sec)
Clean lead vocal
Lead + backing vocals
Full band
Congregation singing
Instrumental section
Pastor speaking
Repeated chorus
Skipped verse
Tempo increase
Temporary audio loss